## Main Page
June 18, 2016 Production Migration Plan
Master Release # TBD
Key Release Teleconference #: For all offical Release Activitites
OBI Project Teleconference #: For all OBI Project Participants
Standard Zone Time for all times shown: | Eastern Daylight Time (EDT)
Key Room: | Conference call
Meetings - update
6:30 | Release Meeting
8:15 | Release Meeting
10:00am | Release Meeting
Saturday 5 pm | Production Logs Validation
Sunday 12 pm | Production Logs Validation
LEGEND
TBD
TBD

## PRE-IMPLEMENT. PLAN
Pre-Implementation Tasks
Segment | Step | QA, Prod, Both | Application | Date | Activity | Owner | SLA | Dependency | Comments | Status | Next Steps | RIT
Database & Data Migration | 1 | QA/Prod | H2O |  | DATABASE | DBA |  |  | QA - Complete PROD -Complete | PENDING
| 1 | QA/Prod | UCFE |  | DATABASE | DBA |  |  | QA - Complete PROD -Complete | PENDING | - Any Maint team DB changes?
WebLogic Server | 2 | QA/Prod | H2O |  | WEBLOGIC - No Change required in 8/27 Scope | WL Team |  |  | QA - Complete PROD -Complete | COMPLETE
| 2 | QA/Prod | UCFE |  | WEBLOGIC - No Change required in 8/27 Scope | WL Team |  |  | QA - Complete PROD -Complete | COMPLETE
Webserver/Webhosting/Repiweb | 3 | QA/Prod | H2O |  | Webserver Proxy Rules - Standalone H2O is working - Need to setup for reverse Bundle Flow | Ty/ Kavya |  |  | * QA - Complete * PROD - Pending | PENDING | - Pinkoo to confirm if setup is complete; we can anyway only test on D-day
| 3 | QA/Prod | UCFE |  | Webserver Rules forUCFE 2.0 - Standalone : Working on QA/PROD - Bundle : Workin on QA/PROD (Routing from UCFE to H2O) | Ty/ Kavya |  |  | * QA - Complete * PROD - Pending | CONFIRMATION REQUIRED | - Pinkoo to confirm if setup is complete; why is Start Bundle going to Prod H2O env, and not within same domain? Is anything pending?
Oracle Coherence cluster | 4 | QA/Prod | H2O |  | Setup new coherence servers for H2O - Logfilename to be corrected (log4j.xml) - to be verified | EHQ DEV Team |  | @CTO Env Eng – PI Distributed <CTOEnvEngPIDistributed@thehartford.com> | * QA - Pending * PROD - Pending | PENDING | 1. Logfilename to be corrected (log4j.xml) - to be verified - 6/13 - Pinkoo/aravind
| 4 | QA/Prod | UCFE |  | Setup new coherence servers for UCFE2.0 - Logfilename to be corrected (log4j.xml) - to be verified | EHQ DEV Team |  | @CTO Env Eng – PI Distributed <CTOEnvEngPIDistributed@thehartford.com> | * QA - Pending * PROD - Pending | done
Fatwire | 5 | QA/Prod | H2O/UCFE |  | Setup Fatwire : - Move H2O content - Move CSC content - Move UCFE2 content Sharepoint location: Fatwire access to Daal Goyal Configurations: none | Daal Goyal |  | Fatwire Console URL : http://csmgmt2.thehartford.com/cs/wem/fatwire/home | * QA - Complete * PROD - Pending | PENDING | > Daal to create a change tracker (since soft release) > Prod day support will be provided by Daal?
Site minder | 6 | QA/Prod | H2O |  | Setup siteminder policy and access for new H2O secure URLs: - 1. http://homequotetestpage.thehartford.com/homesales/* 2. Add rules to protect /homesales/PaymentProcessor/V2 URL pattern | Pinkoo/Aravind |  | Support Team : @ISD Metadirectory Team ETSDMetadirectoryTeam@thehartford.com – Siteminder | * QA - Complete * PROD - Pending | CONFIRMATION REQUIRED
| 6 | QA/Prod | UCFE |  | Setup siteminder policy and access for new UCFE secure URLs: 1. /sales/PaymentProcessor/V2 URL pattern | Pinkoo/Aravind |  | Support Team : @ISD Metadirectory Team ETSDMetadirectoryTeam@thehartford.com – Siteminder | * QA - Complete * PROD - Complete | COMPLETE
Akamai (CDN Setup) | 7 | QA/Prod | H2O |  | > Validation Pending for H2O and UCFE Content > Domain setup (Akamai) | Ty/L2 Team |  | @CTO Env Eng – PI Distributed <CTOEnvEngPIDistributed@thehartford.com> | * QA - Complete * PROD - Pending | PENDING
| 7 | QA/Prod | UCFE |  | > Validation Pending for H2O and UCFE Content > Domain setup (Akamai) | Ty/L2 Team |  | @CTO Env Eng – PI Distributed <CTOEnvEngPIDistributed@thehartford.com> | * QA - Complete * PROD - Pending | PENDING
F5 Rules | 8 | QA/Prod | H2O |  | Setup the folllwing: 1. Load balancing and F5 URLS Creation (DONE) 2. H2O Application PROD URL (RIT raised) 3. H2O to Payment Processor iRules (RIT raised) 4. Redirect HomeLite path to H2O (TODO - RIT) |  |  |  | * QA - Complete * PROD - Pending | CONFIRMATION REQUIRED
Tealeaf Setup/Access | 9 | QA/Prod | H2O |  | Tealeaf Dashboard Setup Tealeaf Acess to team | Sammi |  |  | * QA - Complete * PROD - Pending | PENDING
Logs Setup / Access | 10 | QA/Prod | H2O |  | Access to Production Logs Validate Logs on ENV and DB |  |  |  | * QA - Complete * PROD - Complete | COMPLETE
AppConfig Setup | 11 | QA/Prod | H2O |  | Move Appconfig from QA to PROD - Keys Added as per R2 Scope | Manmohan / Aravind |  |  | * QA - Complete * PROD - Pending | PENDING
| 12 | QA/Prod | UCFE |  | Move Appconfig from QA to PROD - Keys Added as per R2 Scope - UCFE1 DB to be updated in PROD | Manmohan / Aravind |  |  | * QA - Complete * PROD - Pending | PENDING | - ?
AHP Setup | 13 | QA/Prod | H2O |  | AHP: Need to remove cyclic dependencies pi_sales_cdn_content and pi_cdn_content | Peter/Ty |  |  | * QA - Pending * PROD - Pending | PENDING
| 13 | QA/Prod | H2O |  | AHP: Need to remove cyclic dependencies pi_ucfe_war | Peter/Ty |  |  | * QA - Pending * PROD - Pending | PENDING
Dynatrace | 14 | QA/Prod | H2O |  | Dyantrace configuration - Weblogic : Done - Confirm for Coherence |  |  |  |  | CONFIRMATION REQUIRED | Required for Coherence as well.
| 14 | QA/Prod | UCFE |  | Dyantrace configuration - Weblogic : Done - Coherence : Done |  |  |  |  | COMPLETE | Required for Coherence as well.
LogLogic | 15 | QA/Prod | H2O |  | LogLogic configuration |  |  |  |  | PENDING | For R2 LogLogic setup planned for R2 - Pinkoo/Salman to validate accesss to logs with offshore team - Salman to share Dev team details for access with Aravind. Aravind to raise ISSR.
| 15 | QA/Prod | UCFE |  | LogLogic configuration |  |  |  |  | PENDING | For R2 LogLogic setup planned for R2 - Pinkoo/Salman to validate accesss to logs with offshore team - Salman to share Dev team details for access with Aravind. Aravind to raise ISSR.
Blaze | 16 | QA/Prod | UCFE |  | > directory creation for UCFE2-specific rules deployment > AHP job update allowing deploy of rules for UCFE |  |  |  |  | COMPLETE
PDA | 17 | QA/Prod | UCFE | [6 empty] | CONFIRMATION REQUIRED
FS | 18 | QA/Prod | UCFE | [6 empty] | CONFIRMATION REQUIRED
Other Components | 19 | QA/Prod | UCFE | [6 empty] | CONFIRMATION REQUIRED

## IMPLEMENTATION PLAN
Segment | Step | ENV | Start Time | Expected End time | Activity | Owner | Ticket # | Duration (Minutes) | Dependency | Comments | XREF | Status
Verification | 0 | PROD | 2016-06-16 |  | Verify all pre-implementatins task on production servres | L2/WL/WH/DBA Teams
RIT | 0 | PROD | 2016-06-16 |  | Create RIT for Deployment
PRE_PROD ACTIVITY
Appconfig | 1 | PROD | 2016-06-17 23:00 |  | App config New Keys only- H2O
Fatwire | 2 | PROD | 2016-06-17 23:00 |  | Fatwire changes for Release – New Content only(H2O) | Daal Goyal
Database | 3 | PROD | 2016-06-17 23:00 |  | DBA to take backup of the database
Appconfig | 4 | PROD | 2016-06-17 23:00 |  | App config Updated Keys-UCFE2 (validate)
Fatwire | 5 | PROD | 2016-06-17 23:00 |  | Fatwire changes for Release – Updated ContentUCFE2 (validate) | Daal Goyal
Shutdown Application Servers | 6 | PROD | 2016-06-17 23:30 |  | Shutdown Weblogic Server for H2O Application WL URL : http://lad1wlahp2007:22400/console Server : lad1wlahp2007 and lad1wlahp2008 Instance : prod-h2o_m01 and prod-h2o_m02 | WL Team
PROD DAY DEPLOYMENT
Database | 7 | PROD | 2016-06-17 23:30 |  | DBA to execute DDL & DML | Manucher/DBA |  |  |  | 1. DML - Ref Data population from QA/Central Ref data, 2. DML - Y/N indicatator (defaults) - CONSUMER_CRENDENTIAL 2. DDL - Constraints, New columns
Deployment | 8 | PROD | 2016-06-18 03:00 |  | Deploy pi_sales_cdn_content | L1/L2 Team
H2O - send email for Akamai Refresh (Ramesh & Aravind)
RIT : TBD
Build Life ID : TBD
Deployment | 9 | PROD | 2016-06-18 03:00 |  | Deploy pi_cdn_content | L1/L2 Team
H2O - send email for Akamai Refresh (Ramesh & Aravind)
RIT : TBD
Build Life ID : TBD
Deployment | 10 | PROD | 2016-06-18 03:00 |  | Deploy pi_rules | L1/L2 Team |  |  |  | Add validation step
RIT – TBD
Build Life ID : TBD
Deployment | 11 | PROD | 2016-06-18 03:00 |  | Deploy pi_ucfe_cachemanager | L1/L2 Team |  |  |  | Synchronize with Maintenance team on these steps so that cache and application deploys happen for UCFE and H2O consistently
Cohernece Restart
RIT : TBD
Build Life ID : TBD
Deployment | 12 | PROD | 2016-06-18 03:00 |  | Deploy pi_paymentprocessor | Brijesh/App Deployment Team |  |  |  | Synchronize the deploy with other teams (Nitin sharma)
RIT – TBD
Build Life ID : TBD
PaymentProcessor- send email for Akamai Refresh
Deployment | 13 | PROD | 2016-06-18 03:00 |  | Deploy pi_h2o_web | WL Team |  |  | 7,8,9,10
RIT – TBD
Build Life ID : TBD
Bring up the Home Online application with release code
Deployment | 14 | PROD | 2016-06-18 03:00 |  | Deploy pi_ucfe_web | WL Team |  |  | 7,8,9,10
RIT – TBD
Build Life ID : TBD
Bring up the UCFE2.0 application with release code
Deployment | 15 | PROD | 2016-06-18 03:00 |  | Deploy pi_reconciler | L1/L2 Team
RIT – TBD
Build Life ID : TBD
Check Reconciler Logs
Deployment | 16 | PROD | 2016-06-18 03:00 |  | Deploy pi_channelsetupservice | L1/L2 Team
RIT – TBD
Build Life ID : TBD
Bring up the CSU application with release code
Deployment | 17 | PROD | 2016-06-18 03:00 |  | Deploy pi_csc_cdn_content | L1/L2 Team
RIT – TBD
Build Life ID : TBD
Send Akamai Refresh
Deployment | 18 | PROD | 2016-06-18 03:00 |  | Deploy pi_csc_cachemanager | L1/L2 Team
RIT – TBD
Build Life ID : TBD
Coherence Restart
Deployment | 19 | PROD | 2016-06-18 03:00 |  | Deploy pi_csc_web | L1/L2 Team
RIT – TBD
Build Life ID : TBD
Bring up the CSC application with release code
POST Deploymnet Activity
Sanity | 13 | PROD | 2016-06-18 03:00 |  | Verify Dependent Applications UCFE EHQ CSC PaymentProcessor Reconciler | WL /EE Team
Sanity | 14 | PROD | 2016-06-18 03:00 |  | 1) Verify Weblogic Console 2) Verify Server .out logs 3) Verify Cohernece logs 4) Verify Application logs | WL/Dev Team
Sanity | 15 | PROD | 2016-06-18 03:00 |  | Allow Direct trx | Dev Team
Sanity | 16 | PROD | 2016-06-18 03:00 |  | QA team to run a few Direct trxs and notify trx IDs to IM team for IM team to filter out | QA
Sanity | 17 | PROD | 2016-06-18 03:00 |  | Switch Off Direct trxs | Dev Team

## Version - Log (hidden)
Current Version: | 2st QTR 2009
Revision Log: | Date | Enhancements | Revisions made by:
| 2009-04-06 | Content Tab Revised: Deleted Legend, Deployed Unit Name, changed Unit, Added Remedy INC # , Revised Work Classification to financial classidfication and removed ITG reference (tool retired) . | Kelly Majka | Q2 release book is required for all release activity 4/20/2009 and later
| 2009-06-24 | Corrected header for Implementation Tab - spelling error | Kelly Majka
|  | Corrected column on content Tab. Information spelled incorrectly | Kelly Majka
Note on B3: Allways filter/sort in descending order to have most recent changes on top.

## Core Leads (hidden)
| Lead Contact | Recommender for area | Final Decision for area
Wipro | Amar Sharma | Amar Sharma | Shailesh Tiwari | yes
UCFE | Vannak Sin | Vannak Sin | Vannak Sin | yes
BRS MidTier | Tim Neri | Kelly Johnson | Tim Neri | yes
BRS Baskets | Bernie Dube | Kelly Johnson | Bernie Dube | yes
PLA | Umakant Patel | Umakant Patel | Brian Wallace | yes
Testing Solutions Rate Changes | Lisa B |  |  | yes
Documentium | Karthikeyan A J | Karthikeyan A J | Karthikeyan A J | yes
IM Mfg | Savvy Katham |  |  | yes
IM Dataservices - MLS | Brian Embacher | Brian Embacher | Brian Embacher | yes
WTX | George Conklin | George Conklin | George Conklin | yes
QA | Ganesh | Ganesh | Amy Hawkins | yes
IT Project Management | Brian Cutino | Brian Cutino | David Turner | yes
Client | Carlos Aponte | Carlos Aponte | Carlos Aponte
Click to Call | Leena Jobanputra | Leena Jobanputra | Leena Jobanputra
Netinsight | Win Hayes | Win Hayes | Win Hayes
Data Power | Michael Voiland (via Mobile) | Michael Voiland (via Mobile) | Michael Voiland (via Mobile)
MQ | Parthasarathy, Sathyanarayanan
OWSM | Archana Hari | Archana.Hari@thehartford.com
WMB | Parthasarathy, Sathyanarayanan
ISD | Christina Behnken
DBA | Kumar, Tribhuvan (CTO and Service Mgmt); | Ganjikota, Veerendra (Shared Services)
Kana | Rob Foxx | Rob Foxx | Rob Foxx
Architecture | Karen Jurzyck | Karen Jurzyck | Karen Jurzyck
Business Operations | Lynn Orlando | Lynn Orlando | Lynn Orlando
Business Lead | Molly Johnston | Molly Johnston | Molly Johnston
Business PM | Beth Tolan

## Temp sorted by app (hidden)
Segment | Step | Date | TIME | Activity | Owner | Role | Duration (Minutes) | Dependency | Comments | XREF | Status
BRS | BRS - 1 | 2013-10-05 | prior to 6AM | BRS: PWS and Rule execution exports (pre release) (BRS will have separate task list combined for multiple projects - Release doc to be provided by Distributed Support) | Distributed Support
BRS | BRS - 2 | 2013-10-05 | 2:15-3:00 AM | BRS: ODS table transfers (BRS will have separate task list combined for multiple projects) | DBA/ODS
BRS | BRS - 3 | 2013-10-05 |  | BRS: PWS and Rule execution exports (post release) | Distributed Support
BRS | BRS - 4 | 2013-10-05 | 6:05am | BRS: Smoke test | Kelly Johnson | BRS BA
BRS | BRS - 5 | 2013-10-05 | prior to QA Team testing | BRS: Receive notification that all components have been migrated successfully to Production | Kelly Johnson | BRS BA
Client | Client - 1 | 2013-10-05 | 2:00AM | Bring down the region (CICS/IMS) | Brazil | Brazil | 15 |  | done automatically
Client | Client - 3 | 2013-10-05 | 2:00AM | Front End Deploy - Presentation, CommFW | Renee Purdy, Darrell Lapham | Distributed Support | 30
Client | Client - 4 | 2013-10-05 | 2:00AM | Deploy Data Power Code | Michael Voiland | Data Power | 15
Client | Client - 5 | 2013-10-05 | 2:30AM | Flush Cache | Michael Voiland | Data Power | 15
Client | Client - 7 | 2013-10-05 | 3:00AM | Apply DBLs | Sue Chalmers | Data Management | 15
Client | Client - 8 | 2013-10-05 | 3:15AM | SQL Refresher | Sue Chalmers | Data Management | 15 | Client - 7
Client | Client - 9 | 2013-10-05 | 3:15AM | Close PRS move requests (Hartford modules and DBRMS) | Gowtham Shankar, Premkumar Vinayagam | PLATS | 30 | (Client - 2) - not EASE | (except DBA's prs move) HIGEMSG2425CLTD, HIGEMSG2425CLTC, HIGEMSG2425CLT
Client | Client - 10 | 2013-10-05 | 3:45AM | Close DBAs prs move request | Gowtham Shankar, Premkumar Vinayagam | PLATS | 15 | Client -9 | DBAs will notify PLATS to close PRS move.
Client | Client - 11 | 2013-10-05 | 4:30AM | Bring up the region (CICS/IMS) | Brazil | Brazil | 30 | all above
Client | Client - 12 | 2013-10-05 | 5:30AM | Developer Pre QA checkout | Carlos/ Keerthana | Client Team | 30 | Client - 11
Client | Client - 13 | 2013-10-05 | 6:00AM | QA Checkout | QA Team | QA Team | 60 | Client - 12
Client | Client - 14 | 2013-10-05 | 7:00AM | Go no Go decision | EASE Team, Client team | All | 15 | Client - 13
Client | Client - 15 | 2013-10-05 | 12:00PM | MCS Cleanup | MCS Team | MCS Team |  | Client - 14
PDA | PDA - 1 | 2013-10-05 | 6:00AM | Wait for confirmation from PDA team that , PDA has completed processing all the transactions |  | IBM WebLogic | 5
PDA | PDA - 2 | 2013-10-05 | 6:05AM | Stop Process Integrator so that live transactions do not flow through XCP until the deployment is completed. |  | IBM WebLogic | 2 | PDA - 1
PDA | PDA - 3 | 2013-10-05 | 6:07AM | Stop the JMS instances Stop the xpression instances Deploy xpression jar Execute DQL | Jeff Romel | HIG Environment Engineering 10093713 and 10011717 | 3 | PDA - 2
PDA | PDA - 4 | 2013-10-05 | 6:10AM | Deploy DARs | Jeff Romel | HIG Environment Engineering 10093713 and 10011717 | 15 | PDA - 3
PDA | PDA - 5 | 2013-10-05 | 6:25AM | Stop BAM | Vishal Arora | IBM WebLogic | 3 | PDA - 4
PDA | PDA - 6 | 2013-10-05 | 6:28AM | Stop the Content Servers Stop the doc brokers | Jeff Romel | HIG Environment Engineering | 10 | PDA - 5
PDA | PDA - 7 | 2013-10-05 | 6:38AM | Start xpression servers and install pdpx | Jeff Romel | HIG Environment Engineering | 3 | PDA - 6
PDA | PDA - 8 | 2013-10-05 | 6:41AM | Start BAM | Vishal Arora | IBM WebLogic | 4 | PDA - 7
PLA | PLA - 4 | 2013-10-05 | prior to 6AM | Move new DB2 table (THO_BSE_PRFFRMREC). | DA Physical |  |  |  | Existing Table THO_BSE_STROLLPDCD to Production is taken care of by step 10.
PLA | PLA - 5 | 2013-10-05 | prior to 6AM | DB2 Binds - check DBRM'S | Matt/Sandhya
PLA | PLA - 6 | 2013-10-05 | prior to 6AM | SFE : Check SFE changes are in Production. | Matt/Sandhya
PLA | PLA - 7 | 2013-10-05 | prior to 6AM | BRS : Check BRS changes are in Production. | Matt/Sandhya
PLA | PLA - 8 | 2013-10-05 | prior to 6AM | PPM # 1221429: Check BRS PLA upgrade project are in production. | Matt/Sandhya |  |  |  | EASE has a dependency on this code being here. Without this, we will not receive the 'required count' of signatures.
PLA | PLA - 9 | 2013-10-05 | prior to 6AM | PLA: Move PLA copybooks (wr# HIG2423CPYAUTO and ODS10052013) to production | PLATS
PLA | PLA - 10 | 2013-10-05 | prior to 6AM | PLA: Move PLA modules (wr# HIG2423PGMAUTO & HIG1005EADBLAUT) to production. | PLATS |  |  |  | HIG1005EADBLAUT covers the THO_BSE_STROLLPDCD table to production.
PLA | PLA - 11 | 2013-10-05 | prior to 6AM | Verify the AA8065PP module has been compiled as DATA 31. | Matt/Sandhya
PLA | PLA - 12 | 2013-10-05 | 6:00AM | Run the datamap utility to confirm all of the copybooks successfully made it to the production libraries. Compare the datamaps and verify that no displacements have occurred. | Matt/Sandhya
PLA | PLA - 13 | 2013-10-05 | 6:00AM | Run the LINKDT utility to confirm all of the modules successfully compiled to the production libraries. | Matt/Sandhya
PLA | PLA - 14 | 2013-10-05 | 6:15AM | Email QA Team that PLA Changes are successfully compiled to Production with DB2 tables. | Matt/Sandhya
PROOF | PROOF - 1 | 2013-10-05 | 3:00AM | Release PROOF code in Production servers | Manintenance team | Developer | 15 | None
PROOF | PROOF - 4 | 2013-10-05 | 6:30AM | End to end testing by QA | QA | Tester |  | EASE & all upstream code deploy successful

## Contacts
Confirmed? | Application | Manager | Name | Location If you can commute to windsor you should be onsite for the prod release | Contact# | Pager / Alternate Phone / Email - Comments
CSC
| UBS |  |  |  |  | Also working WebLogic upgrade at 11:30 pm Fri 11/20
UBS
UBS
TABS
Database: no changes
PDA
PDA
PDA
Env Engineering for PDA changes
Tealeaf
Maxymiser
Fatwire
Datapower
Stratigent
OBI - CSC
Payment Processor
YES | WebLogic
YES | Env Engineering (Deployment)
YES | MBM Team
Previous:
| ACS team – Distributed support |  | Distributed support | Offshore | 860-843-6262 | CTO Env Eng – L1 Windows;@CTO Env Eng – PI Distributed;@EITSM ACS PI DISTRIBUTED HIG
877-283-8066 - option 8 - option 1
| Kenneth Herren |  | Release Manager | Onshore | 877-283-8066 - option 8 - option 2 | 203-577-9138 (c)
Offshore
| Crystal O’Connor |  | Release Manager | On site | (860) 547-7138 | Cindy update with Ranjani's info
| Francisco J Castellanos |  | Tech Lead | On site
| Cynthia E Webb |  | OBI-PM | On site | 860-751-4712
| A J Karthikeyan |  | Documentum -Primary |  |  | 860 899 5465 @WCM Support
| Michael Voiland |  | Data Power |  | 860-547-2837 | Pager 866-257-9616
| Frank Punzo |  | Platform Architect |  | 860-843-6712 | 860-302-1208 c/860-621-0876 h
| Indira Chitrapu |  | ISD Web Hosting |  |  | @ISD IBM Web Hosting
| ISD Weblogic Server team |  |  |  | 860-843-6943 | @ISD Weblogic_Team
| Mark Fagan |  | PLATS |  | 860-547-4231
| AJ, Kartikeyan |  | Documentum - ECM |  | TBD | (860) 208-2638 C/860-942-8225 H
| Mazzotta, Dean |  | Program Architect |  |  | 860-844-8741
| Meenakshi Narayanan |  | Oracle Data Services |  |  | @PLC PLA DA-Physical
| Prabu Pitchai |  | Foundation Services |  |  | 312-823-0954 C/860-842-9865(Pager)
| Sivashakthi Chinnadurai |  | APP DBA |  |  | @MBM MDS PI
| Shahina Rahman |  | App Owner |  |  | 203-228-1834
| Winthrop Hayes |  | Web Analytics
| Manucher Sasani/ Rita A Kirby |  | DBA |  |  | TBD
| Keith Gallicchio |  | TEALEAF |  | TBD | TBD
| Ed Morelli |  | GOMEZ |  | TBD | TBD
| Ali Salman Rizvi |  | Sapient Sr. Architect | Onshore | TBD | TBD
| Sharvan Bhatt |  | Sapient Architect | Offshore | TBD | TBD
| Sandeep Dahiya |  | Sapient PM | Offshore | 91 9811695395 | TBD
| Anil Raina |  | Sapient QA Lead | Offshore | TBD | TBD
| Anna Goulet |  | OBI-DBA | Remote | cell: 860 227 7093
| Daal Goyal |  | OBI-Fatwire | Offshore
| Victor Dias |  | CSC Maxymiser Test Events | New York | (914) 844-1575 | mailto:victor.dias@maxymiser.com or contact cell phone - call or txt
| Ram |  | QA | Onshore | 8605432528
Environment Engineering
Note on F3: William Zielinski: if applicable

## Release Defects
|  | Release Day Issues |  |  | Priorities: Critical-must be fixed today or we back out High-fix in tues emergency rls. Med / Low: Fix during warranty.
# | Category | Issue | owner | Status | Notes | Priority | Incident #
20 | Log error | Parsing issue with payment date | Renjith / Swamy / Sharvan | Dup | 50+ payments impacted. Ramesh is copying payment processor logs, then Pinkoo and Francisco will analyze. UBS response for payment activity has 2 different date formats - inconsistent. Sharvan will send details. Possibly check dynatrace in QA to see if this happened during testing. | tbd - need to know impact
30 |  | Customer clicked once, charged twice | Renjith | Monitor | Monitor logs for duplicate and failed payments, both EFT and credit card. Renjith needs policy #. 55pht760838 Renjith confirmed there was a duplicate payment. As of 10:35 am this was the only dup payment 11:10: 2 duplicate payments have been logged: Sue's acct. Time difference ~ 1 - 16 sec. 11:25 renjith: Root cause unknown. Daneil can stop payments. Prod has been haing duplicate payment issues. An incident was already submitted. Currently: goes into work queue. If cust hasn't overpaid acct, will let payment go thru. Examples listed were Sue's, and not actual duplicates. There was a prod incident from 9/28 that s/have fixed this.: INC000020267302 TABS team will send to Daneil to check.
40 |  | UI issues |  | Closed | Was cuased by incorrect URL for CDN content.
50 |  | Unable to pay by credit card - blanks not opened up |  | Closed
60 | Log error | Parsing issue with next payment date | Sharvan | Dup | Express Pay flow: an exception is showing on the logs: error parsing next payment date. Not known whether any customer impact. AJ will look in tealeaf. BAN 64201338 9:38 am Renjith: not related to the UBS service. Happens when cust does zip code validation. A similar error: Error parsing payment date. Pinkoo: degrades gracefully; impact to customer not expected. Code s/be changed to be able to handle blank dates. Pinkoo: check into whether a timeout could have caused the exception / parsing error, or use of Back button. There are exceptions pre-dating the release. May have been falsely logged as an error. No aparent cust impact. | Med
70 |  | Sue didn't receive confirmation email on her Express Pay payment | PDA team | Closed | Jasmine's team lookng into
80 | Log error | Payment amount null - can see in logs | Sharvan | Dup | Research. May be related to timeouts. Usually comse with the parsing error (#60) | tbd - need to know impact
90 | Performance | Customer waited for payment to complete for more than 60 seconds |  | Closed | To investigate, need to know if cust is on a landline, mobile, etc. 55RBE577015 Came from a cust complaint. Can't tell if something was down etc due to release activity. 9:53 am last page Closed pendng further occurrences
100 | Log error | From error log: A problem occurred while attempting to access the property last payment amount. | Sharvan | Dup | To be investigated
130 | Performance | Francisco sees some peaks Sat related to billing info service | Swamy | Hold | Already an incident - performance issue related to BACIS DB link issue. May be unrelated to OBI. | N/A
140 | UI

## Tags
Component/Application | SVN REPO | TAG URL
pi_core
pi_email_component
dc_commonutils
pi_bomodel
pi_contentmanager
pi_serviceproxy
pi_ucfe_serviceproxy
pi_businessdto
pi_businessservice
pi_sales_controller
Pi_secured_web
pi_h2o_war
pi_cdn_content
pi_csc_common
Application | AHP Project | Build Life
H2O | pi_rules
pi_ucfe_cachemanager
pi_sales_cdn_content
pi_h2o_web
UCFE | pi_rules
pi_ucfe_cachemanager
pi_cdn_content
pi_ucfe_web
pi_ucfe_reconciler
Payment Processor | pi_paymentprocessor
CSC 2.0 | pi_csc_cachemanager
pi_csc_web
pi_csc_cdn_content

## IMPACTED SYSTEM
Impacted Systems | Scope | MTE Ticket Id
PLA | 1. Issue with follow up 2. MBM changes - Akila to talk to DB2 team to ensure PROD database tables would be refreshed
Foundational Services | 1. FS team to confirm the release 2. AD1 Group Id.
Data Power | 1. Whitelisting of H2O user id and password. 2. Subsription for PDA email for client 3. WMB for Exceed calls
UCFE Database | 1. H2O Reference Database 2. UCFE Schema Constriants 3. UCFE DDL for CCTable 4. UCFE DML for CCTable
Payment Processor | 1. New Web Proxy Rules to Support H2O context root.
CSC 2.0 | 1. App Config 2. Fatwire Changes 3. Code packet
UCFE 2.0 | 1. Web Proxy Conguration to Support Bundle 2. F5 Rules to Support Payment Processor Redirection 3. Siteminder protecion for homesale/PaymentProcessor URL pattern 4. Repliweb Configuration (for Web Content) 5. ADB Directory on each servers 6. Fatwire 7. Code Package
H2O 1.0 | 1. Webserver Proxy Rules 2. Repliweb Job Setup 3. Coherence 4. Weblogic 5. Test Page Setup (siteminder, iplanet and web proxy) 6. Akamai 7. F5 Rules for Payment Processor 8. Siteminder protecion for homesale/PaymentProcessor URL pattern 9. ADB Directory on each servers 10. Dynatrace and Loglogic Setup 11. Fatwire Content & Landing Page 12. Code pakcage
Fatwire | 1. UCFE Code and Content Pakcage 2. HH2O Code and Content Pakcage 3. CSC Code and Content Pakcage
PEGA | ?
BRS -- Endorsement Rule Service | HH2O Rules
BRS (via PLA) | HH2O Underwriting Rules
CLIENT | 1. Client Service 2. Contact History 3. WMB 4. Mainframe
KANA | 1. Email Quote Configuration for AARP
Tea Leaf
Click to Chat
Tealium
Centralized Ref Data (PROD)
Opion Lab
MLS | NA
CAFÉ | ?
Home Light | 1. Webserver Redirection
PDA | 1. Two New Templates 2. One Existing Templates
HIG.Com | 1. Landing pages 2. HIG.con drop down (form submit)